## Blad1
Timeframe | Ticket | Priority level (low-medium-high) | Time (# hours) | Category (preparation, organisation, input, code, output, reporting) | Assigned to | Review (1 per sprint)
Sprint 1 (1 september)
| Group formation | low | 0 | organisation | Everyone | no comments
Sprint 2 (8 september)
| Contact with company supervisor - Plan meeting to ask questions about certain columns | medium | n/a | input | Wendy, Quinten | improve communication between us and teaching team and company
| Data exploration - First look at the dataset and getting familiar with it | high | 0.5 | preparation | Everyone
| Setup GitHub | low |  | organisation | Quinten
Sprint 3 (15 september)
| Data exploration (spillover) - First look at the dataset and getting familiar with it | high | 2 | preparation | Everyone | Create more structure
2025-09-16 | Meeting with company supervisor - Expectation management and discussing our end result | high | 0.5 | organisation, input | Quinten, Reno, Wendy
2025-09-17 | Group meeting - Data cleaning,determine which columns are relevant | high | 2 | input | Everyone
| Schedule meeting with TA | low | n/a | organisation | Wendy
| Project proposal - Make a base for proposal | medium | 1 | reporting | Quinten
| Project proposal - Finish chapter 2: data preprocessing | medium | 0.5 | reporting | Reno
| Project proposal - Finish chapter 1: introduction, chapter 3: backlog and make additions to chapter 2: data preprocessing | medium | 1 | reporting | Wendy, Rosanne
Sprint 4 (22 september)
| Clean sample data - Write code to read and clean dataset | high | 2 | code | Rosanne | Improve communication with teaching team and company, normalise data, see what works for us in terms of backlog
2025-09-22 | Group meeting for proposal - Finish document | medium | 1 | reporting | Everyone
2025-09-23 | Meeting with TA - First meeting - Feedback on our work so far | medium | 1 | organisation | Everyone
| Assign project manager - To keep clear overview of our progress and clear communication | medium | n/a | organisation | Everyone: Wendy= PM
| Create user stories | low | 0.5 | preparation | Rosanne
| Create requirement list | low | 0.5 | preparation | Rosanne
| Submit project proposal | high | n/a | reporting | Quinten
| Create tickets in GitHub - More structured way of project management | low | 0.5 | organisation | Wendy
| Fix the sprint tasks - Make sprint tasks more specific | medium | 0.5 | organisation | Wendy
| Write a project backlog diary - Important for project management and reporting | high | 1 | organisation | Wendy
| Think of a funny joke for next meeting - Good for group cohesion | low | n/a | organisation | Quinten
| Visualisations on cleaned data - Clear view on the trends of the data | medium | 1 | code | Quinten
| Make some tests on the cleaned data - Get familiar with updated dataset | high | 1 | code | Reno
Sprint 5 (29 september)
| Write a sprint review for each sprint - Nice to know what to keep into account for next sprint | low | 0.5 | reporting | Everyone | We acted quickly with the missing data
| Upload documents to Github - Clear overview in one place | medium | 1 | organisation | Wendy
| Finish processing the data - Make data binary, categorical or numerical | high | 2 | code | Reno
| Try to run a regression model | high | 2 | code | Rosanne
| Make visualisations that support the research question - Data evaluation of cleaned data and visuals of statistics | medium | 1 | code | Quinten
| Write an explanation on the visualisation | low | 0.5 | reporting | Wendy
Sprint 6 (6 october)
10 October Midterm
Sprint 7 (13 october)
Sprint 8 (20 october)
Sprint 9 (27 october)
Make powerpoint for final presentation
Sprint 10 (3 november)
4 November Project deadline